## Sheet1
DIRECTORS SITE SAFETY/ HEALTH/
WELFARE LOSS PREVENTION
INSPECTION REPORT
Job Detail: | K30131 - DeVere Gardens
Page 1 of 2 | Date: | 17/02/2014
Site Address:
DeVere Gardens, 1 Victoria Road, London W8 5AF |  |  |  | Director | Graham Cox
|  |  |  | Client | Second London Wall
Site manager | Rosemary Young |  |  | Principle Contractor | Sir Robert McAlpine
Recieved By: | Rosemary Young |  |  | Signature: | Graham Cox
Accident Summary |  |  | Priority Action
Since Previous Audit |  |  | Summary |  | No. | Points | Totals | Site Score
Category |  | Number | Priority S - DANGER- |  | 0 | 4 | 0 | Max Points
Site Hours Monthly (Feb) |  | 1665 | STOP WORK IMEDIATELY |  |  |  |  | Achievable
Major Injury |  | 0 | Priority A |  | 0 | 3 | 0 | /100 = R
O/7 Day |  | 0 | IMEDIATE RECTIFICATION |  |  |  |  | Points Achieved
U/7 Day |  | 0 | Priority B |  | 0 | 2 | 0 | /R = T
Dangerous Occurence |  | 0 | RECTIFICATION WITHIN 24HRS |  |  |  |  | 100 - T =
First Aid Only |  | 0 | Priority C |  | 0 | 1 | 0
Damage/ Near Miss |  | 0 | RECTIFICATION WITHIN 72HRS
|  |  |  | TOTALS | 0 |  | 0 | Site Score
[8 empty] | 100 | %
Safety Planning Provisions: |  | √ - No Action Required At Present S - Stop Work A - Imediate Action Required
B - Action Required Within 24hrs C - Action Required Within 72 hours X - Not Applicable * - Other Comment
Principle Contractor Requirements Only
1.Statuary Notices & Signs |  | √ | 2.Construction H&S Plan |  | X | 3.HASAW Poster |  |  | √
4.Welfare - Canteen/Prep. |  | √ | 5.Welfare-Drying,Changing facilities |  | √ | 6.Welfare-Toilets/Washing |  |  | √
7.Site Security/Public Protecion |  | √ | 8.Entry/Exit Procedure (Sign In/Out) |  | √ | 9.Traffic Mangement |  |  | √
10.Fire/Planning/Extinguishers |  | √ | 11.First Aid/Emergency/Accident info |  | √ | 12.Lighting |  |  | √
General Audit
1.Insurance/Test Certs |  | √ | 2.Method Statements |  | √ | 3.Risk Assessments |  |  | √
4.Method Statements-S/C |  | √ | 5.Risk Assessments-S/C |  | √ | 6.Launguage Control Measures |  |  | √
7.Induction Training |  | √ | 8.Vibration Usage Records/Info/Tags |  | X | 9.Lifting Plan |  |  | √
10.QA Documentation up to date |  | √ | 11.Environmental-Waste Control |  | √ | 12.Environmental-Animal |  |  | X
13.Electricity-Supply/Equipment |  | √ | 14.Equipment/Material-Delivery Control |  | √ | 15.Construction Material Storage |  |  | √
16.Portable Tools/P.A.Tests |  | √ | 17.COSHH/Flammable Materials/Storage |  | √ | 18.Lifting Equipment Storage |  |  | √
19.WAH-Safety/Permits |  | X | 20.Training Certification (SGB) |  | √ | 21. Training Certification (S/C) |  |  | √
22.Ladder/Scaffold Inspection |  | √ | 23.Scaffold Guardrails/Edge Protection |  | √ | 24.LOLER Inspection |  |  | √
25.PUWER Inspections |  | √ | 26.Height Safety/Equipment/Inspection |  | X | 27.Harness Inspection |  |  | X
28.Crane Inspection |  | X | 29.Noise-Control & hearing Protection |  | X | 30. Tower Scaffold/Set Up |  |  | √
31.Leading Edges |  | X | 32.Personnel Training Records(cscs etc) |  | √ | 33.Toolbox Talks |  |  | √
34.P.P.E-Onsite Usage |  | √ | 35.Housekeeping |  | √ | 36.Acess/Egress On Site |  |  | *
37.Hot Works/Safety/permits |  | √ | 38.Smoking |  | √
General Comments & Future Guidance: |  |  |  | All personnel were found with good PPE, Exclusion Zones were
being ignored by other trades, most notably the dry-liners
Site Description: |  | Site was in reasonably good condition in most areas, some access issues were observed
with materials observed being carried up staircases in block C
Page 2 of 2 | Job Detail | K30131 | Address: | DeVere Gardens, 1 Victoria Road, London W8 5AF
Director |  | Graham Cox |  |  | Date | 2014-02-17
Recieved By: |  | Rosemary Young |  |  | Signature
Hazard Description |  | Trades were observed carrying materials up the staircase in Block C
36*
Recommendations |  | SRM to issue TBT requirement to ensure trades do not carry materials up emergency access
Staircases
Priority |  | S |  | A | B |  |  | C
Actions Taken
Hazard Description
Recommendations
Priority |  | S |  | A | B |  |  | C
Actions Taken
Hazard Description
Recommendations
Priority |  | S |  | A | B |  |  | C
Actions Taken
Hazard Description
Recommendations
Priority |  | S |  | A | B |  |  | C
Actions Taken