## Sheet1
SITE SAFETY/ HEALTH/ WELFARE
LOSS PREVENTION INSPECTION
REPORT
Job Detail: | K16060 - Leicester Square
Page 1 of 2 | Date: | 02/03/2016
Site Address: | 48 Leicester Square, London
|  |  |  | Safety Consultant | Jeremy Bromley
|  |  |  | Client | Linseed Assets Limited
Site manager | Dominic Conaghan |  |  | Principal Contractor | Brookfield Multiplex
Received By: | Kevan Rasen, Dominic Conaghan |  |  | Signature: | Jeremy Bromley
Accident Summary |  |  | Priority Action
Since Previous Audit |  |  | Summary |  | No. | Points | Totals | Site Score
Category |  | Number | Priority S - DANGER- |  | 0 | 4 | 0 | Max Points
Site Hours Monthly (March) |  | TBC | STOP WORK IMEDIATELY |  |  |  |  | Achievable
Major Injury |  | 0 | Priority A |  | 2 | 3 | 6 | /100 = R
O/7 Day |  | 0 | IMEDIATE RECTIFICATION |  |  |  |  | Points Achieved
U/7 Day |  | 0 | Priority B |  | 1 | 2 | 2 | /R = T
Dangerous Occurrence |  | 0 | RECTIFICATION WITHIN 24HRS |  |  |  |  | 100 - T =
First Aid Only |  | 0 | Priority C |  | 0 | 1 | 0
Damage/ Near Miss |  | 1 | RECTIFICATION WITHIN 72HRS
|  |  |  | TOTALS | 3 |  | 8 | Site Score
[8 empty] | 94.8718 | %
Safety Planning Provisions: |  | √ - No Action Required At Present S - Stop Work A - Immediate Action Required
B - Action Required Within 24hrs C - Action Required Within 72 hours X - Not Applicable * - Other Comment
Principle Contractor Requirements Only
1.Statuary Notices & Signs |  | √ | 2.Construction H&S Plan |  | √ | 3.HASAW Poster |  |  | √
4.Welfare - Canteen/Prep. |  | √ | 5.Welfare-Drying,Changing facilities |  | √ | 6.Welfare-Toilets/Washing |  |  | √
7.Site Security/Public Protection |  | √ | 8.Entry/Exit Procedure (Sign In/Out) |  | √ | 9.Traffic Management |  |  | √
10.Fire/Planning/Extinguishers |  | √ | 11.First Aid/Emergency/Accident info |  | √ | 12.Lighting |  |  | √
General Audit
1.Insurance/Test Certs |  | √ | 2.Method Statements |  | √ | 3.Risk Assessments |  |  | √
4.Method Statements-S/C |  | X | 5.Risk Assessments-S/C |  | X | 6.Launguage Control Measures |  |  | X
7.Induction Training |  | √ | 8.Vibration Usage Records/Info/Tags |  | X | 9.Lifting Plan |  |  | √
10.QA Documentation up to date |  | √ | 11.Environmental-Waste Control |  | √ | 12.Environmental-Animal |  |  | √
13.Electricity-Supply/Equipment |  | √ | 14.Equipment/Material-Delivery Control |  | √ | 15.Construction Material Storage |  |  | √
16.Portable Tools/P.A.Tests |  | √ | 17.COSHH/Flammable Materials/Storage |  | √ | 18.Lifting Equipment Storage |  |  | √
19.WAH-Safety/Permits |  | √ | 20.Training Certification (SGB) |  | √ | 21. Training Certification (S/C) |  |  | √
22.Ladder/Scaffold Inspection |  | X | 23.Scaffold Guardrails/Edge Protection |  | A | 24.LOLER Inspection |  |  | √
25.PUWER Inspections |  | X | 26.Height Safety/Equipment/Inspection |  | X | 27.Harness Inspection |  |  | √
28.Crane Inspection |  | X | 29.Noise-Control & hearing Protection |  | X | 30. Tower Scaffold/Set Up |  |  | B
31.Leading Edges |  | X | 32.Personnel Training Records(cscs etc.) |  | √ | 33.Toolbox Talks |  |  | √
34.P.P.E-Onsite Usage |  | √ | 35.Housekeeping |  | √ | 36.Acess/Egress On Site |  |  | A
37.Hot Works/Safety/permits |  | X | 38.Smoking |  | √
General Comments & Future Guidance: |  |  |  | Works in progress on levels 2-7 observed.
Site Description: |  | Site was generally clean and tidy with the exception of the external scaffold on levels 2-5.
Page 2 of 2 | Job Detail | K16060 | Address: | 48 Leicester Square, London
Safety Consultant: |  | Jeremy Bromley |  |  | Date | 02/03/2016
Received By: |  | Kevan Rasen, Dominic Conaghan |  |  | Signature | Dominic Conaghan
Hazard Description |  | External Scaffold on levels 2-5 was found to have numerous equipment & materials
left loose and at risk of falling onto lower levels or to external public areas due to missing
23 | * | toe boards and gaps as well as creating trip hazards. Scaffold tubes at waist & head
height creating significant impact risks as not clearly identified by warning tape or
signage. (see accompanying photos)
Recommendations |  | Report the PC BM for their scaffold contractor and staff to rectify
Priority |  | S |  | A | B |  |  | C
Actions Taken |  | Reported to BM
Hazard Description |  | Operative found on tower scaffold incorrectly built with platform too high and missing
30 |  | toeboards
Recommendations |  | Report to Cornelius manager, operative to be issued verbal warning and considered for
WAH Safety retraining.
All personnel to receive TBT on WAH Safety.
Priority |  | S |  | A | B |  |  | C
Actions Taken
Hazard Description |  | Access to external scaffold provided by PC BM through window on level 2 east elevation
36 | * | leads out onto railed window ledge with no safe way of accessing scaffold.
No gate access provided by BM to allow SGB personnel to access work areas
requiring personnel to have to climb over scffold
Recommendations |  | A safe method of access such as a tied ladder should be provided for access onto the
external scaffold.
Access gates to be provided for safe access to inner external scaffold.
Priority |  | S |  | A | B |  |  | C
Actions Taken
Hazard Description
Recommendations
Priority |  | S |  | A | B |  |  | C
Actions Taken
Hazard Description
Recommendations
Priority |  | S |  | A | B |  |  | C
Actions Taken
Hazard Description
Recommendations
Priority |  | S |  | A | B |  |  | C
Actions Taken